SUBIECTE 2021

1.

Let’s first see what the predecessors of each activity should be

| Create Network Diagram | Create Activity List |
| --- | --- |
| Create Project Scope | - |
| Create WBS and WBS dictionary | Determine Quality Standards |
| Determine Critical Path | Create Network Diagram |
| Develop Budget | Estimate Time and Cost |
| Estimate Time and Cost | Determine What to Purchase |
| Gain Formal approval of the plan | Plan communication |
| Hold kick-off meeting | Gain formal approval of the plan |
| Determine what to purchase | Estimate resource requirements |
| Plan communications | Determine Roles and responsibilities |
| Determine Roles And Responsibilities | Estimate Time and Cost |
| Determine quality standards, process and metrics | Create project scope statement |
| Create Process Improvement Plan | Determine quality standards, process and metrics |
| Perform Risk Identification | Develop Budget |
| Estimate Resource requirements | Determine Critical Path |
| Create activity List | Create WBS |

| Activity | Previous activity |
| --- | --- |
| Create Project Scope Statement | - |
| Determine Quality Standards, process and metrics | Create Project Scope Statement |
| Create WBS and WBS dictionary | Determine Quality Standards, process and metrics |
| Create activity List | Create WBS and WBS dictionary |
| Create Network Diagram | Create activity List |
| Determine Critical Path | Create Network Diagram |
| Estimate resource requirements | Determine Critical Path |
| Determine what to purchase | Estimate resource requirements |
| Estimate time and cost | Determine what to purchase |
| Develop budget | Estimate time and cost |
| Perform risk identification, .... | Develop budget |
| Determine roles and responsibilities | Perform risk identification, .... |
| Plan communications | Determine roles and responsibilities |
| Gain formal approval of the plan | Plan communications |
| Create Process improvement plan | Gain formal approval of the plan |
| Hold kick-off meeting | Gain formal approval of the plan |

2.

I think that the most important process the could have prevented this is the Continuous Delivery Process. This process would have assured the fact that the sponsors get the project at different stages and functioning standards weekly or so (depending on sprint time).
Having this opportunity, the sponsors could have said earlier that the product does not comply with their standards and some changes could have been done. 
This leads us to the Continuous Delivery Agile process (embrace change) which could have also solved this situation.

Another process that could have prevented the incident is the QA process in which the product is tested and the “quality of the product is assured” meaning that the requirements (both functional and non-functional) have been checked and the system meets the requirements.

3.

Possible critical paths:

A B D E H =2+2+2+4+1=11
A C D E H =2+4+2+4+1=13
A C F G H =2+4+4+3+1=14 => CRITICAL PATH

8 days passed, A completed, C only 75%

100/person/day

Scheduled: 8 days => 800/person , solve A, solve C, solve F 50%  => BCWS = 800

Actual: 8 days => 800/person, solved A, solved C 75% => BCWP = 500 ( because, A=2 days => 200, 75%C = 3 days => 300)

SV = BCWP – BCWS = 500 - 800 = -300 <0 => behind schedule

4.

12 weeks, 100.000

6 weeks passed, 60.000 spent, 40% done

BAC = 100.000

BCWS = 6/12 * 100.000 = 50.000

BCWP = 40% * 100.000 = 40.000

ACWP = 60.000

SPI = BCWP / BCWS = 40.000 / 50.000 <1 => behind schedule

CPI = BCWP / ACWP = 40.000 / 60.000 <1 => over budget

For EAC assume the same performance index as until now.

EAC = ACWP + (BAC – BCWP)/CPI = 60.000 + (100.000 – 40.000) *3/2 =~ 150.000 (150.909–with 0.66)

5.

BAC = 360.000

AC = ACWP = 120.000

EV = BCWP = 180.000

ETC = 145.000

EAC = actuals to date + new estimate for remaining work

EAC = AC + ETC = 265.000

Or

CPI = BCWP / ACWP = 180.000 / 120.000 = 3/2 => under budget (>1)
EAC = AC + (BAC - BCWP)/CPI

= 120.000 + (360.000 – 180.000) * 2/3 = 240.000

6.

- Authority without responsibility

For example, an expert consultant which is not part of the organization has authority in his/her domain (knows a lot) but it is not responsible.

- Responsibility without accountability

From RACI we can say that the project team has the responsibility to take part in the project planning but the team is not accountable for that plan. The project manager is accountable for that one.

- Accountability without responsibility

For example, the General Manager of a company is accountable for everything that happens to the company. Lets say that an employee breaks some system of something in the company/organization. The one that is accountable for that is the manager, even if he was not the one responsible for the bad action.

7.

The organizational structure is weak matrix.

In such a structure, the Project Manager has limited authority and control over the resources, and works part-time.

Moreover, the budget is controlled by the Functional Manager.

8.

Use-cases:

- View depth information gathered from stereo video sequence

- View obstacles in the path

- Detect  stop signs, traffic lights and dangerous situations which could imply an accident

UUCW

- UC1 -> simple

- UC2 -> average

- UC3 -> complex

- UUCW = 1*5 + 1*10 + 1*15 = 30

UAW

Only 1 actor, the end user, operates the application via cmd => UAW = 1

TCW

9.

CPI = ?
CPI = BCWP / ACWP

BCWS = 2

BCWP = 75% * 2 (the original task was for 2 persons) = 1.5

ACWP = 1 (only 1 person assigned to do the task)

CPI = 1.5 /1 = 1.5  => under budget (>1)

SPI = BCWP / BCWS = 1.5 / 2 = 0.75 => behind schedule (<1)

10.

8 months, 200.000 total cost

4 months passed, 120.000 spent, 40% work done

Performance index not applicable => EAC_2

BAC = 200.000

BCWS = 4/8 * 200.000 = 100.000

BCWP = 40% * 200.000 = 80.000

ACWP = 120.0000

EAC = ACWP + (BAC – BCWP) = 120.000 + 120.000 = 240.000

11.

EV = BCWP = 600

AC = ACWP = 650

PV = BCWS = 560

SV = BCWP – BCWS  = 600 – 560 = 40 > 0 => ahead of schedule

CV = BCWP – ACWP = 600 – 650 = -50 <0 => over budget

CPI = BCWP / ACWP = 600 / 650 = 0.92 <1 => over budget

12.

12 weeks

Total cost 100.000

6 weeks passed, 60.000, 40% done

BAC = 100.000

BCWS = 6/12 * 100.000 = 50.000

BCWP = 40% * 100.000 = 40.000

ACWP = 60.000

Performance index will remain the same => 
EAC_3 = ACWP + (BAC – BCWP) / CPI

CPI = BCWP / ACWP = 4/6 = 2/3 < 1 => over budget

EAC_3 = 60.000 + (100.000 – 40.000) * 3/2 = 150.000

13.

BAC = $100.000 for 10 days project

Day 6, 70% performed, 65.000 spent

- BCWS = 6 / 10 * 100.000 = 60.000

- BCWP = 70% * BAC = 70.000

- ACWP = 65.000

EV =  BCWP = 70.000

BAC = 100.000

CPI = BCWP / ACWP = 70.000 / 65.000 > 1 => under budget

SPI = BCWP / BCWS = 70.000 / 60.000 > 1 => ahead of schedule

14.

4 days, 4000

Day 3, 3500, 70%

BAC = 4000

BCWS = ¾ * 4000 = 3000

BCWP = 70% * 4000 = 2800

ACWP = 3500

EV = BCWP = 2800

BAC = 4000

SPI = BCWP / BCWS = 2800 / 3000 < 1 => behind schedule

CPI = BCWP / ACWP = 2800 / 3500 < 1 => over budget

15.

AC = ACWP = 4.000.000

CV = BCWP – ACWP = -500.000 => BCWP = CV + ACWP = 3.500.000

SPI = BCWP / BCWS = 1.12 => BCWS = BCWP / SPI = 3.125.000

BAC = 9.650.000

EV = BCWP = 3.500.000

PV = BCWS = 3.125.000

CPI = BCWP / ACWP = 3.500.000 / 4.000.000 = 0.875

Variance typical =>

EAC_3  = AC + (BAC – BCWP)/CPI

= 4.000.000 + ( 9.650.000 – 3.500.000 ) / 0.875 =~ 11.028.571

16.

Same as 15.

WBS